## Slide 1: Joint Master Thesis - Modelling of production expertise to extend the data-driven analysis of process models
Supervisor:
Prof.Dr.ir. Wil van der Aalst
Advisors:
  Mahsa Pourbafrani MSc
  Marco Schopen MSc

## Slide 2: Schedule
All the work in defining deviation, problems, bottlenecks, … in process mining. (you should have done it by now, you can also perform more research and complete that)
Work includes papers, codes, software, Prom plugin ….
Designing the Taxonomy of the problems based on the current works, knowledge, and everything that you could find (1 week)
Note that this is the scientific part of your work as a master thesis which is mandatory
Since we are behind the schedule, I would suggest to send us the result or have a meeting in 10 days let’s say!
Draw the framework of your work (2 days)
When you have the idea and the taxonomy you can do it shortly.
Remaining logic coding (Cleaning, Timestamp identification, Scoping of the log, + role and decision-related weakness identification)-1 week
Integration and testing with different types of logs -1 week
Design + Development of UI + integration with backend logic – 2 weeks
Testing end to end with different flows – 1 week
Presentations and applying the suggestions - 2 weeks
Writing of thesis – 4 weeks
Limited availability due to part time work -3 weeks
Total-14 weeks ( approx. 3-4 months)

## Slide 3: Taxonomy
Cases
Events
Activity
Process
Instance of
Instance of
Log
Unwanted Activity
Back-loop
Incorrect resource
Parallelizable tasks
Bottle Neck
Variance of Process Time
Idle time
Interface or media change
Redundant Activity
Eventually Follows

## Slide 4: Framework
Event Log
Cleaning, Timestamp identification, Sorting, Scoping of the log
Identify the weakness(10 main+ role and decision related)
Expert input for weakness identification
Dataframe as excel indicating weakness and its occurrence level
UI